Version 3.1

Last Edited by Mitchell Sayer
10/08/20

Production Plan

Production Plan Document

Contents

Tasks, Responsibilities and Assets	2

Team Members & Responsibilities	2

Project Goals	2

Project Burndown	3

Project Timeline/ Schedule	4

Milestones	5

Pre-Production	5

Alpha	5

Beta	5

Gold	5

Lessons Learnt Log	6

Risk Assessment Process	10

SWOT	10

Risk Likelihood	10

# Tasks, Responsibilities and Assets

## Team Members & Responsibilities

| Name | Role | Responsibility |
| --- | --- | --- |
| Mitchell Sayer | Game Designer | - Production Coordinator - Narrative Design - UX Feel/ Experience Designer - Sound Design - Level Design - Character balancing |
| Richard Delamore | Game Programmer | - Mechanic Building - Source Control monitoring - Systems Creator |
| Tiana Knobloch | Character & UI Artist | - Character Modelling - Character Animation - UI Art Design - Cinematic Animator - Concept Art - Texturing Assets |
| Daniel Iaria | Tech Artist | - Particle Effects - 3D Modelling - Procedural Texturing - Texturing Assets |
| Joshua Freeman | Environmental & Foliage Artist | - Environmental Art/ Set Dressing - Foliage Modelling and Placement - Texturing Assets |

## Project Goals

- To create a memorable experience for the target audience

- Providing the player to create their own innovative comedic moment

- Develop an enjoyable game that has smooth replayablity.

- Design and produce a product from all team members strengths.

- Publish the game on Epic Games Marketplace

- Port to different platforms i.e.: IOS, Android, Nintendo Switch.

## Project Burndown

The following graph visually underlines the estimated process of the project’s execution and how well the team will achieve its goals

## Project Timeline/ Schedule

| Milestone | Sprint & Date |
| --- | --- |
| Pre-Production | Week 1PP (20th - 22nd July) - Concepts Made Week 2PP (27th - 28th July) - Grey boxing Prototype building Week 3PP (3rd - 5th Aug) - Prototype complete + Pitch |
| Alpha | Week 1A (10th - 11th Aug) - Level 1 Grey boxed - Character Modelling Started - Environment Level 1 Started Modelling Week 2A (17th - 19th Aug) - Character Rigging Started - Level 2 Grey boxed - Environment Level 2 Modelling Week 3A (24th- 25th Aug) - High Poly Refinement Process Started Week 4A (31st Aug- 2nd Sept) - Level 3 Grey boxed - Environment Level 3 modelling Week 5A (7th - 8th Sept) - UI implemented Week 6A (14th - 16th Sept) - Foliage addition 1st pass Week 7A (21st - 22nd Sept) - All levels meet 1st pass standards - Character Rigged and Modelled - All Mechanics built - QA Testing |
| Beta | Week 1B (28th Aug - 30th Sept) - Character Animation Started - Debugging Process Started - Set dressing Started Week 2B (5th - 6th Oct) - Character Textured Week 3B (12th - 14th Oct) - Character Animated - Set dressing finalised Week 4B (19th - 20th Oct) - Light Baking Week 5B (26th - 28th Oct) - Assets Textured - Audio Refined - All bugs fixed |
| Gold | Week 1G (2nd - 3rd Nov) - Polish Everything Week 2G (9th - 11th Nov) - Release Date |

# Milestones

## Pre-Production

- Grey-boxing

- Prototype Mechanics built

- Prototype built

## Alpha

- All game levels blocked out, grey boxed, and first passed

- Audio Implemented

- Character Model

- Character Rig

- High Poly Refinement Process

- All Mechanics Built

## Beta

- Cutscenes Designed

- Set dressing

- Character Animated

- Character Textured

- Light Baking

- Texturing Overall

- Bug fixing

## Gold

- Polish Levels

- Polish Assets

- Polish Mechanics

- Create Teaser Clip

# Lessons Learnt Log

| Feedback: | How to Improve on it |
| --- | --- |
| Keep your concepts simple and effective. | Keeping ideas simple and easy to execute |
| Alexandra Mannel: - Love the idea of the ghost game it sounds fun with the aspect of going around scaring people as ghosts. Would it be better if you were looking through the camera as you move? - 3rd game not really a fan Neil Boyd: - The Hand game I see as being a fun game to run around with the ragdoll movement of the hand physics - You need to make sure there is a clear line of sequencing for the body building part. - The Ghosts game I’m confused about the jump scares for a kid’s game, it doesn’t really sit well with that target audience, if it were a mature audience it could work but not for a kid’s game. - That would need to be focused and designed to work around that limitation. Paco Casares: - Ghost game with the multiplayer is a good unique selling point however the setup of multiplayer can take time depending on experience making it. - Taking into consideration games like Project Zero could be good as reference. Jesse Donlevy: - Hand Concept is doable as there’s room to add more art assets and levels and the replayablity is high - The Ghost game the same as well its safe, and different levels add complexity/ variety to gameplay. Myles Blasonato: - Love the hand idea as well it kind of reminds me of Katamari with the whole evolving size aspect, with the items impacting the player. - The arena fighter is a lot to consider technically and from a designer perspective it would only be a slice of gameplay - With the ghost idea the theme needs to be fixed as it doesn’t make sense with the pillars in place. | Utilise on the strengths of all ideas and work on the second idea. Keep concepts simple and work to teams strengths. |
| Tiana Knobloch: - Character Model - Janky movement due to mesh collisions Daniel Iaria: - Character Movement won’t be possible because of skeletal mesh errors Character Mesh & Animation | Find an alternative to showcase the character creation without the need of controlling it. Making the player feel good about what they made regardless of the result. |
| - Competitive Market Research - Emotion in Pillars | Perform further research into competitors and seek why the weakness are what they are and improve of them. Draw a story from the pillars of the game and make sure they concrete the concepts goal. |
| - Replayablity, Character movement, Player Goals - Game Vision | Look for ways to show variety to the player whilst not having to change the game dramatically. |
| - Don’t detour from original concept: You’re not making a fashion flash game - The original body building is innovative, stay with that. It’ll lead to good results. | Taking a step back to overlook what has been discussed is a great way to get back on track. |
| - Make sure version is before not after in UE4 to avoid conflicts in opening the project file. | Take more care in using game engines and prepare before hand to start projects with less launch issues. |
| - Font text colour needs to be changed - Too much text on the alpha, beta, gold slide, simplify it. - Make sure the game titles are fixed | People have short attention spans, keeping info short and simple is key. |
| - Voice pitch needs to be practiced on - Change the name of the persona - Practice on timing | Be louder and prepare more before presenting in future. |
| - It can be done there is a setting in blueprints that allows you to move without mesh collisions. | Apply newly found information to solve problems. |
| - Should think about the levels in which your size can dictate where you can go if that unlocks more items or can reach. Can unlock new areas. | Relook at level designs and play with the idea of mechanics. |
| - Guudo’s UFO concept needs brighter colours closer to what his head looks like, whites and light greys | Brighten up the darker areas of the UFO such as the wings and the cockpit, make them brighter whites and off whites |
| - Everyone speaks well - Don’t move hands when presenting its distracting - Don’t need all art information in the gold section of milestones, nothing should be touched. - Don’t need to include preferred language of coding - Narrative setting is required if it's an important element of discussion. - Slow down - Explain the item collection further - Gold should focus on marketing and packaging the product. | Follow given advice |
| - Art shows a lot of promise - Would be good to have a prototype of shaders, try swapping out the noise factor in the existing shader. - Lighting scale is good idea in art - Proof of foliage in the environment would make a stronger presentation - Including a finished asset would assist the strength of the presentation - Physics was unclear how it would be used. - A clearer and refined schedule would be nice to use as reference to allow a better scope prediction. - No foliage concepts or block outs to be seen. Mentioned in PowerPoint and would be nice to see concepts of them - No proof of art, i.e. Art asset completed in chosen style in engine to showcase game look. - Overall minimum number of concept pieces to showcase environment look. Needed more to show what game looked like before the actual prototype. - Screenshots of the game environment would have been nice to see the idea of level layout. (paint over ideally) - Litter throughout presentation screenshots of gameplay mechanics and loops to give a better idea. - No dates on deliverables - No age demographic in your target market, this is an issue. - Theme is good - Story is nice - Design element was weak: - How do I win? - How do I gain points? - How do I lose? - How do I use my abilities? - What reason do I have to use my abilities? - Level Design concepts would've been nice to see - No explanation of goals. | Foliage proof on concept, modelled and added to UE4 scene to test art style Proof of art Completed And added to engine scene Completed additional concepts of all asset types to be completed Screenshot paint overs added and designed Add in missing information in future, and discuss clearly about how the game should look, play, and its goals alongside its execution and ending conditions. |

# Risk Assessment Process

## SWOT

## Risk Likelihood

[Low Risk: 1 – High Risk: 5]

| Risk | Likelihood | Cause of Risk | Response to Risk |
| --- | --- | --- | --- |
| Over Scoping | 3 | High Ambitions | Maintain a simple idea. Create an enjoyable, small project. Wishlist tasks can be added later if need be. |
| Resistance to Change | 2 | Too attached to an idea or concept | Reach an alternative that simulates both strengths and reasonability for execution. |
| Stress & Anxiety | 3 | Strict Deadlines/ Difficulty executing ideas and concepts | Maintain appropriate weekly workload and stick to schedule timings. Avoiding unnecessary tasks that detour from original task schedule. |
| External commitments | 4 | External commitments to the workplace | Proactive planning to avoid missing workdays/ Preparing and updating plans beforehand to avoid having no work to continue with. |
| Corrupt files | 3 | Not saving/ backing up save data often, incorrect version control, damaged hard drives, source control errors | Frequent checking on Source Control and maintain version control on Engine to make sure projects do not become corrupted |
| Not meeting deadlines | 1 | Procrastination, distractive environments, lack of confidence | Introduce new activities/ tasks each day that could make working enjoyable. Avoid sites that could lead to distraction, set a timer for how quickly you can complete a task swiftly and efficiently. |

# Change Log

## Version 1.0

Base foundation of documentation including headings and sections for the following:

Tasks, Responsibilities and Roles

- Team Members and Responsibilities

- Project Goals

- Project Burndown

- Project Timeline/Schedule

Milestones

- Pre-Production

- Alpha

- Beta

- Gold

Lessons Learnt Log

Risk Assessment Process

- SWOT

- Risk Likelihood

## Version 2.0

All information added to their respective sections. Information provided should be read carefully to fully understand intentions and direction of the project.

## Version3.1-

Added:

- Project Burndown Charts; Project Overview, Alpha, Beta, Gold